# Underperforming Store Improvement Initiative

Operational Excellence Program

Date: January 2025

Classification: Internal - Operations

________________________________________________________________________________

# Executive Summary

Analysis of Q4 2024 performance identified 8 underperforming stores requiring intervention. These locations represent $12.4M in annual revenue (9.7% of total) but operate at 22% below company average on key metrics. This plan outlines a 90-day turnaround initiative targeting 18-25% improvement through merchandising optimization, training enhancement, and local market activation.

# Underperforming Store Portfolio

## Tier 3 Performance (Bottom 8 Stores):

## 1. Oklahoma City (l-10)

Q4 Revenue: $980K (Target: $1.4M) - 30% below target

Daily transactions: 89 (Target: 145)

Average ticket: $11.20 (Target: $13.80)

Customer satisfaction: 3.8/5.0 (Target: 4.3+)

Employee turnover: 47% (Company avg: 18%)

Root causes: Poor location visibility, limited foot traffic, staff training gaps, inventory misalignment

Action plan: Relocate to Bricktown district (Q2), intensive staff training, revise product mix to favor value segment

## 2. Tulsa (l-23)

Q4 Revenue: $1.1M (Target: $1.5M) - 27% below target

Daily transactions: 102 (Target: 158)

Average ticket: $10.80 (Target: $13.80)

Customer satisfaction: 3.9/5.0

Key issue: Aging store design, limited parking

Action plan: $180K renovation (February-March), improve parking signage, local marketing campaign, staff incentives

## 3. El Paso (l-36)

Q4 Revenue: $1.0M (Target: $1.45M) - 31% below target

Daily transactions: 95 (Target: 148)

Average ticket: $10.50 (Target: $13.80)

Customer satisfaction: 3.7/5.0

Cultural fit: Product assortment not aligned with Hispanic market preferences

Action plan: Introduce dulce de leche, tamarind, and chamoy flavors. Bilingual staff training. Partner with local quinceañera planners for gift segment

## 4. Fresno (l-49)

Q4 Revenue: $1.15M (Target: $1.5M) - 23% below target

Daily transactions: 108 (Target: 153)

Average ticket: $10.65

Customer satisfaction: 4.0/5.0

Issue: Strong local competition from regional chains

Action plan: Price competitive audit, loyalty program aggressive promotion, exclusive Central Valley flavors (almond-based given regional agriculture)

## 5. Albuquerque (l-32)

Q4 Revenue: $1.08M (Target: $1.48M) - 27% below target

Daily transactions: 99 (Target: 150)

Average ticket: $10.90

Customer satisfaction: 3.8/5.0

Issue: Staff engagement low, high theft rates

Action plan: Replace store manager, implement security improvements, introduce Southwest flavor profile (green chile chocolate, piñon nut offerings)

## 6. Mesa (l-39)

Q4 Revenue: $1.2M (Target: $1.55M) - 23% below target

Daily transactions: 115 (Target: 159)

Average ticket: $10.45

Customer satisfaction: 4.1/5.0

Issue: Proximity to Phoenix store causing cannibalization

Action plan: Differentiate assortment vs Phoenix (focus value tier), target families with kids-oriented products, weekend sampling events

## 7. Long Beach (l-48)

Q4 Revenue: $1.25M (Target: $1.6M) - 22% below target

Daily transactions: 118 (Target: 162)

Average ticket: $10.60

Customer satisfaction: 4.0/5.0

Issue: Underutilized tourist traffic potential

Action plan: Tourist-focused merchandising (gift boxes, grab-and-go), partnerships with hotels, multi-language signage, Instagram-worthy displays

## 8. Sacramento (l-12)

Q4 Revenue: $1.3M (Target: $1.65M) - 21% below target

Daily transactions: 125 (Target: 168)

Average ticket: $10.40

Customer satisfaction: 4.1/5.0

Issue: Mall location with declining foot traffic

Action plan: Evaluate street-level relocation, aggressive digital marketing to drive destination traffic, host in-store events (candy-making workshops)

# 90-Day Turnaround Plan (January-March 2025)

## Phase 1: Assessment & Quick Wins (Days 1-30)

Week 1: Deploy operations team to each store for diagnostic assessment

Week 2: Implement immediate fixes (signage, cleanliness, merchandising resets)

Week 3: Begin staff training intensive (customer service, product knowledge, upselling)

Week 4: Launch local marketing campaigns, optimize inventory to local preferences

## Phase 2: Strategic Interventions (Days 31-60)

Week 5-6: Execute renovations (Tulsa priority)

Week 7: Introduce regional/local exclusive products

Week 8: Implement new incentive programs for staff

Week 9: Review progress, adjust tactics based on early results

## Phase 3: Optimization & Validation (Days 61-90)

Week 10-11: Fine-tune assortment based on sales data

Week 12: Scale successful tactics across all 8 stores

Week 13: Final assessment, determine next phase (sustain or escalate)

# Merchandising Optimization Strategy

## Current Problems:

Over-indexed on premium tier ($4+) in price-sensitive markets

Insufficient representation of local/regional flavor preferences

Poor shelf positioning of high-velocity items

Inconsistent planogram execution

## Solutions:

Rebalance mix: 40% value ($1-2.50), 35% core ($2.50-3.50), 25% premium ($3.50+)

Introduce 3-5 location-specific SKUs per store based on demographics

Place top 10 national sellers at eye level, impulse items at checkout

Weekly audits by district managers with photographic compliance tracking

# Enhanced Training Program

## Product Knowledge Academy:

4-hour intensive: History and crafting of each product family

Flavor profile descriptions: Enable staff to make recommendations

Allergen and ingredient training: Build customer trust

Sampling techniques: Drive trial and upselling

Certification program with badges and financial incentives

## Customer Service Excellence:

Role-playing scenarios for difficult customer interactions

Upselling techniques: Increase average ticket by $2-3

Gift selection guidance: Capture gifting occasions

Complaint resolution empowerment: Reduce escalations

# Local Market Activation

## Community Engagement:

Partner with 3-5 local influencers per market (food bloggers, lifestyle)

Sponsor local events (farmers markets, festivals, school fundraisers)

Host in-store tastings every weekend (12-4pm)

Create "Local Hero" product featuring hometown flavor

Donate product to local charities (build goodwill, visibility)

## Digital Marketing:

Geo-targeted Facebook/Instagram ads (10-mile radius)

Google My Business optimization (hours, photos, posts)

Yelp review response program (address negative, thank positive)

SMS marketing to local loyalty members (exclusive offers)

TikTok partnership with local creators for viral challenges

# Financial Investment & ROI

## Investment Breakdown:

Renovations (Tulsa): $180K

Merchandising resets (8 stores): $95K

Training program development & delivery: $120K

Local marketing campaigns: $180K

Staffing (temporary operations support): $85K

Technology (POS upgrades, analytics): $65K

Total investment: $725K

## Expected Returns (12-month projection):

Revenue increase: $3.1M (25% improvement on $12.4M base)

Gross margin improvement: 2.5 points (better assortment, less waste)

Customer satisfaction increase: 0.4 points (4.2+ target)

Employee turnover reduction: 50% (saves $180K in hiring costs)

Total financial benefit: $3.8M

ROI: 424% in Year 1

Payback period: 3.2 months

# Success Metrics & Milestones

## 30-Day Targets:

Revenue: +8% vs prior month

Traffic: +12% (marketing activation)

Average ticket: +$0.75 (training impact)

Customer satisfaction: +0.15 points

Staff engagement survey: +20 points

## 60-Day Targets:

Revenue: +15% vs baseline

Traffic: +18%

Average ticket: +$1.50

Customer satisfaction: +0.30 points

Staff turnover: -25%

## 90-Day Targets:

Revenue: +22% vs baseline (stretch: 25%)

Traffic: +25%

Average ticket: +$2.20

Customer satisfaction: +0.45 points (4.2+ achieved)

Staff turnover: -40%

Profitability: Breakeven on investment

# Program Governance

## Leadership Team:

Program Sponsor: VP of Operations

Program Manager: Director of Store Operations

Merchandising Lead: Regional Merchandising Manager

Training Lead: Learning & Development Manager

Marketing Lead: Regional Marketing Manager

Store Managers: Direct accountability for local execution

## Reporting Cadence:

Daily: Store-level dashboards (revenue, traffic, satisfaction)

Weekly: Progress calls with each store manager

Bi-weekly: Steering committee review (leadership team)

Monthly: Executive presentation with full P&L impact

Quarterly: Board update on program results

# Risk Mitigation

Manager resistance: Address through incentives, clear expectations, support

Execution variability: Daily audits, standard operating procedures, peer learning

Market factors: Control what we can, adapt quickly to external changes

Staff turnover during transition: Retention bonuses, improved working conditions

Investment not yielding returns: Kill criteria at 60-day mark if <10% improvement

# Conclusion & Authorization Request

This focused initiative targets our highest-opportunity stores with proven interventions. The combination of merchandising optimization, training investment, and local marketing activation has demonstrated 20-30% improvements in similar retail turnarounds. With $725K investment returning $3.8M in year-one benefits, the business case is compelling. Request approval to proceed with January 15 launch.

________________________________________________________________________________

Prepared by: Store Operations Excellence Team

Reviewed by: VP Operations, CFO, Head of Merchandising

Contact: storeops@sweetstores.com